## Sheet1
JAVA TRAINING PLANNING
Milestone | Task | Description | Estimated Time | Dependency
Setup environment | Install tools | install Docker, GraalVM, PosgreSQL, WSL | 0.5 day
KeyCloak Setup | -KeyCloak research - Configure realm & Client | Research and create KeyCloak Realm and OIDC client | 1 day | Environment setup
Database setup | - Design Database - Setup database | Design and setup database | 0.5 day | Environment setup
API implement | - Design API - Implement API | Design and implement endpoints | 2 day | Database setup
Security Integration | - Research Spring Security - OIDC Integration | Connect Spring Security to Keycloak | 1 day | API implement
Packaging, build and run | - GraalVM research - Docker & Native Build | Create Dockerfile and Compose config | 2 day | Security Integration
Document Writing | Write document | Include API, setup, usage guide | 0.5 day | All previous